## Slide 1
Ndu Project PDOS MVP
Overall Update:
  Project Plan completed
  Project Requirements Document (PRD) completed
  Project Jira set up
  Project schedule pending staffing update
  Project cost pending staffing update
June 2026
Product Managers Activities:
  PRD mapping to project scope completed
  Jira activities ongoing
    Change Epics to Features using provided and agreed on nomenclature
    Reflect Stories per provided guidelines
  Design review for landing page and pharmacy page in progress
Designer Activities:
  Update landing page to reflect new direction
  Implement comments to Pharmacy page when available
Product Design and Marketing Activities:
  Align with designer on landing page and pharmacy page updates
  Commence on design for other pages
  Update project tracking log to reflect status
Web Developers Activities:
  Completed system architecture design
  Waiting on development start
Mobile Developers Activities:
  Waiting on Landing page UI design completion to progress the architecture
  Completed pattern design for mobile app application
Status | Overall | Design | Development | Release
Now |  |  |  | 
Trending |  |  |  | 
On target OR Done
Possible Issues
Major Issues OR Not Started
Not applicable
Recent Accomplishments/Activities:
  Web development architecture and planning complete
  Mobile development architecture complete
  Landing page design almost complete
Planned Activities:
  Finalize landing page design
  Update ADO to reflect Features and group the uploaded corresponding Stories
Issues:
  Overall:-
  Project staffing is causing delay to development start
  Limited Jira functionalities has led to some re-adjustments to process
  Last minute directional change to already reviewed landing page design has resulted in rework
  Reduced transparency on internal decisions that directly impact the project
  Design:-
  Bottleneck to the design process given there is one designer
    May lead to further delays once project team ramps up
  Landing page 1st draft issued
    Review in progress
    Update to a few banners
  Pharmacy page design was scheduled for June 12th review start. This have been delayed.
  Development:-
Dedicated team required to fully start the execution phase