1. Start with a Deliverable-Based WBS

Build a Level 2–4 WBS structured around physical deliverables or systems, not departments.

Example:

- Facility

  - Civil works

  - Structural

  - Mechanical systems

  - Electrical systems

This becomes the backbone for everything else.

For Ndu project, the work breakdown structure goes to the second level

2. Create Engineering Work Packages (EWPs)

From each WBS element, define EWPs that produce the design outputs needed for execution.

EWPs typically include:

- Drawings

- Specifications

- Calculations

- Bill of materials

- Codes

- Requirements

- Etc.

Key principle:

- EWPs must be complete enough to release for execution or construction (for waterfall projects)

For Ndu project, these are the design packages that align with all requirements and applicable specifications. This should come to the 3rd level of the WBS to identify all design and engineering work needed for each of that level of scope.

3. Develop the Procurement & Contracting Breakdown

From EWPs, identify all items that must be purchased or contracted.

Break this into:

- Long-lead equipment

- Bulk materials

- Subcontracts

For each item, define procurement activities:

- Scope definition

- RFQ/RFP

- Bid evaluation

- Award

- Fabrication

- Delivery

This creates a Procurement Breakdown Structure (PBS) aligned to the WBS.

For Ndu project, any design that needs to feed into a procured item needs to be identified in it’s package so that it’s scope it complete for sending to the vendor to build (mostly for waterfall but could be applicable to agile sometimes). This would be at that 3rd level of the WBS as well.

4. Define Execution Work Packages (EWPs) and/or Construction (CWPs)

Translate WBS + EWPs into CWPs, which are executable field scopes.

Each EWP/CWP should:

- Be tied to a specific area/system

- Be executable by one crew or contractor

- Have all prerequisites defined

Prerequisites include:

- Approved IFC (Issued for Construction) drawings

- Materials available

- Permits approved

- Access and site readiness

For Ndu project, the execution work packages could be called construction work packages if there is construction work for that scope. If not, it would be EWP especially for Agile. This also comes down to from the WBS second level all the way to the lowest level possible. Could get to 8 levels if needed until it gets to hours of work level. This work packages usually combine design and procurement or contract scope especially at the 3 to 5th levels.

5. Sequence All Activities (Integrated Logic)

Now connect engineering → procurement → Execution/construction in one network:

Typical logic chain for Waterfall:

- Engineering complete → Procurement start

- Procurement delivery → Construction start

- Construction complete → Commissioning

Example:

- EWP (pipe design) →

- Procure pipe →

- Deliver pipe →

- Install pipe (CWP)

This is where most schedules fail if logic is weak.

For Agile, the packages would be more for iteration, so, the EPICs should have a general estimation based on project duration based. The duration basis (number of iterations) can be based on either historical data OR extrapolation. Each estimated hours/block needs to be backed up in the estimate basis

6. Estimate Durations Across All Domains

Estimate durations for:

- Engineering (design cycles, reviews)

- Procurement (lead times, vendor timelines)

- Construction (crew productivity rates)

Use consistent methods across all three to avoid mismatch.

7. Build the Integrated Schedule Network

Use a method like the Critical Path Method (CPM) to calculate the full timeline.

Key outputs:

- Critical path across engineering, procurement, and construction

- Total project duration

- Float on non-critical paths

This step ensures procurement delays or design bottlenecks are visible early.

8. Align Contracts to Work Packages

Contracts should map cleanly to CWPs and procurement packages:

- Each major CWP → contract or subcontract

- Each procurement package → vendor contract

Avoid:

- Contracts that cut across multiple CWPs (creates coordination chaos)

9. Resource Load and Validate

Check:

- Labor availability

- Equipment constraints

- Vendor capacity

Apply:

- Resource leveling

- Constructability review

10. Develop the Time-Phased Schedule

Convert into:

- Gantt chart with:

  - EWPs

  - Procurement activities

  - CWPs

- Milestones:

  - Design complete

  - Contract awarded

  - Equipment delivered

  - Construction complete

  - Commissioning start

11. Establish Schedule Readiness Rules

A CWP should not start unless all constraints are cleared:

- Engineering complete

- Materials on site

- Permits approved

- Predecessors finished

This is the core of reliable execution planning.

12. Baseline and Control

Baseline the integrated schedule and track:

- Engineering progress vs release dates

- Procurement expediting vs delivery dates

- Construction progress vs planned sequence

Estimate Basis

Estimate Basis for Schedule Development

- Defines the assumptions, methods, and data sources used to determine activity durations across engineering, procurement, and execution

- Scope alignment

  - Estimates are tied directly to WBS elements, EWPs, and CWPs

  - Ensures every duration reflects a clearly defined deliverable or work package

- Estimation methods

  - Expert judgment

  - Historical project data

  - Parametric or productivity based rates

  - Three point estimating where uncertainty is high

- Key assumptions

  - Resource availability and crew sizes

  - Productivity rates and learning curves

  - Working calendars and shift patterns

  - Site conditions and access

- Procurement considerations

  - Vendor lead times

  - Fabrication durations

  - Logistics and delivery constraints

  - Contract award timelines

- Engineering considerations

  - Design complexity

  - Review and approval cycles

  - Iteration and rework allowances

- Constraints and risks

  - Dependencies between engineering, procurement, and construction

  - Long lead or critical items

  - External approvals and permits

  - Known uncertainties and contingency assumptions

- Validation and benchmarking

  - Comparison against similar projects

  - Cross functional review of durations

  - Alignment with the Critical Path Method to ensure logical consistency

- Documentation

  - Clearly recorded assumptions, exclusions, and confidence levels

  - Provides transparency and supports future updates

Core Insight

- The quality of a schedule is only as strong as its estimate basis

- Weak or undocumented assumptions lead to unrealistic timelines and execution failure