Agile Schedule Development Process

This process provides guidance for developing the scheduling capability within the Project Delivery Operating System. The intent is to provide a structured yet flexible framework that allows users to progressively decompose work, plan execution, and manage delivery using agile principles.

The scheduling functionality should support progressive elaboration, rolling-wave planning, iterative delivery, and continuous feedback. Users should be able to move seamlessly from strategic planning to sprint execution while maintaining visibility across all levels of the schedule.

1. Establish the Schedule Basis

The schedule basis defines the rules and assumptions used to create and maintain schedules.

The platform should allow users to define:

Delivery Approach

- Agile or hybrid delivery model

- Sprint duration

- Release cadence

- Increment strategy

Schedule Controls

- Definition of Ready

- Definition of Done

- Dependencies

- Constraints

- Assumptions

- Milestones

- Interfaces

Estimation Methods

- Story points

- T-shirt sizing

- Velocity forecasting

- Capacity planning

Scheduling Principles

The schedule should support:

- Progressive elaboration

- Rolling-wave planning

- Dynamic dependencies

- Continuous reprioritization

- Readiness-based execution

2. Support a Deliverable-Based WBS

The scheduling module should support a deliverable-based hierarchy. Users should organize work around what is being delivered rather than around activities.

The hierarchy should support:

Major Deliverable

↓

Epic

↓

Feature

↓

Story

↓

Task

Each level should inherit information from the level above while allowing additional detail to be progressively added.

3. Support Multiple Schedule Levels

The schedule should be maintained across four levels, allowing users to manage both strategic and detailed work.

Level 1 Schedule – Roadmap

Purpose:

Provide strategic visibility.

The platform should allow users to manage:

- Major deliverables

- Product increments

- Releases

- External commitments

- Key dependencies

- Milestones

The primary planning level should be:

Epics

Level 2 Schedule – Release Plan

Purpose:

Organize work into deliverable increments.

The platform should allow users to manage:

- Releases

- Epics

- Major dependencies

- Interface points

- Milestones

The primary planning level should be:

Epics

Level 3 Schedule – Feature Plan

Purpose:

Translate epics into executable functionality.

The platform should allow users to manage:

- Features

- Engineering Work Packages (EWPs)

- Procurement Packages

- Execution Work Packages (WPs)

- Dependencies

- Interfaces

The primary planning level should be:

Features

Features should:

- Deliver business value.

- Have clear acceptance criteria.

- Minimize dependencies.

- Be capable of being completed within an iteration cycle.

Level 4 Schedule – Sprint Schedule

Purpose:

Support detailed execution.

The platform should allow users to manage:

- Stories

- Tasks

- Acceptance criteria

- Sprint commitments

The primary planning level should be:

Stories

Stories should be executable within a sprint.

4. Support Progressive Work Decomposition

The scheduling module should guide users through progressively breaking down work.

Major Deliverable

↓

Epic

↓

Feature

↓

Story

↓

Task

The UI should encourage decomposition through intuitive workflows and relationships between objects.

Each level should support:

Descriptions

Acceptance Criteria

Dependencies

Interfaces

Owners

Status

Priority

Attachments

Comments

5. Support Work Estimation

The platform should support multiple estimation methods.

Epic Estimation

Epics should support T-shirt sizing.

Available values:

- XS

- S

- M

- L

- XL

Large epics should be decomposed into multiple features.

Feature Estimation

Features should support:

T-Shirt Sizes

- XS

- S

- M

- L

- XL

or

Relative Story Point Ranges

| Size | Approximate Story Points |
| --- | --- |
| XS | 8–13 |
| S | 13–21 |
| M | 21–34 |
| L | 34–55 |
| XL | 55+ |

Features should be small enough to fit within an iteration.

Story Estimation

Stories should support story point estimation using the Fibonacci sequence.

Available values:

1, 2, 3, 5, 8

Story Sizing Guidelines

| Story Points | Relative Size |
| --- | --- |
| 1 | Trivial |
| 2 | Very Small |
| 3 | Small |
| 5 | Moderate |
| 8 | Large |
| >8 | Too Large |

Stories larger than 8 points should automatically trigger recommendations for decomposition.

Stories should be capable of being completed within a single sprint.

Estimation Techniques

The platform should support:

- Planning Poker

- Relative Comparison

- Affinity Mapping

- T-Shirt Sizing

6. Support Engineering Work Packages (EWPs)

Engineering work should be delivered incrementally.

Examples may include:

- Requirements

- Architecture

- Designs

- Specifications

- Models

Each EWP should support:

Definition of Ready

- Inputs available

- Scope understood

- Acceptance criteria defined

- Dependencies identified

Definition of Done

- Deliverables completed

- Reviews performed

- Approvals received

- Ready for downstream use

7. Support Procurement Packages

Procurement work should be managed as incremental packages rather than single activities.

Examples include:

- Scope Definition

- Vendor Selection

- RFQ/RFP

- Evaluation

- Award

- Delivery

- Validation

Long-lead items should be visible and prioritized appropriately.

8. Support Execution Work Packages (WPs)

Execution work represents implementation activities.

Each WP should support:

Definition of Ready

- Engineering complete

- Dependencies resolved

- Inputs available

- Access available

- Approvals received

Definition of Done

- Work complete

- Testing complete

- Acceptance criteria satisfied

- Ready for integration

9. Support Backlog Management

The platform should maintain relationships between:

WBS

↓

Epic

↓

Feature

↓

Story

↓

Task

Users should be able to prioritize work based on:

Business Value

Dependency Relationships

Risk Reduction

Constraints

Long-Lead Activities

Backlogs should support drag-and-drop reprioritization.

10. Support Dependency Management

Dependencies should be visible across all domains.

Engineering

↓

Procurement

↓

Execution

↓

Integration

↓

Testing

↓

Release

Supported dependency types should include:

Finish-to-Start

Start-to-Start

External Dependencies

Interface Dependencies

Dependency impacts should automatically propagate through the schedule.

11. Support Rolling-Wave Planning

The platform should allow users to progressively elaborate work.

Future work should remain at higher levels until sufficient detail exists.

Epic

↓

Feature

↓

Story

↓

Task

Users should be able to continuously refine work throughout execution.

12. Support Iterative Delivery Cadence

The scheduling engine should support configurable sprint durations:

- One week

- Two weeks

- Three weeks

- Four weeks

Two weeks should be the default recommendation.

Sprint Planning

The platform should support:

- Team capacity review

- Prioritization

- Story selection

- Dependency validation

- Definition of Ready verification

- Sprint goal definition

Outputs:

- Sprint backlog

- Sprint goals

Daily Sprint Meetings

The platform should support:

- Progress tracking

- Blocker identification

- Dependency discussions

- Constraint removal

- Team coordination

Outputs:

- Updated sprint board

- Updated blockers

Sprint Execution

The platform should support:

- Task execution

- Collaboration

- Continuous integration

- Continuous testing

- Documentation

Outputs:

- Working increments

Backlog Grooming (Refinement)

The platform should support continuous refinement activities.

Users should be able to:

- Break epics into features.

- Break features into stories.

- Refine acceptance criteria.

- Re-estimate work.

- Reprioritize backlog.

- Prepare future sprints.

Outputs:

- Ready backlog

Sprint Review and Demo

The platform should support:

- Demonstrations

- Stakeholder feedback

- Acceptance validation

- Story approval

Outputs:

- Accepted increment

Sprint Retrospective

The platform should support:

- Lessons learned

- Team feedback

- Process improvements

- Action items

Outputs:

- Continuous improvement actions

13. Support Constraint Management

The platform should provide a visible constraint register.

Constraints may include:

Requirements

Resources

Interfaces

Vendors

Technical Limitations

External Dependencies

Constraint removal should drive prioritization and execution.

14. Support Schedule Performance Metrics

Agile Metrics

The platform should provide:

Velocity

Story points completed per sprint.

Burndown

Remaining work.

Burnup

Completed work.

Throughput

Stories completed.

Lead Time

Request to delivery.

Cycle Time

Start to finish.

Schedule Metrics

The platform should provide:

Milestone Progress

Dependency Health

Forecast Completion

Critical Path Movement

Release Predictability

Schedule Development Flow

The scheduling capability should guide users through the following progression:

Schedule Basis

↓

Level 1 Schedule (Roadmap)

↓

Level 2 Schedule (Release Plan)

↓

Level 3 Schedule (Feature Plan)

↓

Epic

↓

Feature

↓

Estimate and Size

↓

Story

↓

Sprint Planning

↓

Daily Sprint Meetings

↓

Sprint Execution

↓

Backlog Grooming

↓

Sprint Review and Demo

↓

Sprint Retrospective

↓

Rolling-Wave Planning

↓

Next Sprint

↓

Release

Core Principle

The scheduling capability should encourage users to progressively transform strategic objectives into executable work. Epics should decompose into features, features into stories, and stories into tasks. Work should only enter a sprint when it satisfies the Definition of Ready, and stories should be sized so they can reasonably be completed within the selected iteration. Continuous refinement, collaboration, reviews, and retrospectives should ensure schedules remain adaptive while maintaining delivery discipline.

Estimate basis is also required.